[image: image5.emf]• Inpatient 

Documentation,  Order 

Entry and Results 

Retrieval

• Occupational Health 

Surveillance

• Release 1

-Dental Charting and 

Documentation

-Spectacle Request 

Transmission System II

• Release 2

-Ad Hoc Query Ability 

2 

-ACPGs

• Encounter 

Documentation

• Order Entry and Results 

Retrieval 

1

• Encounter Coding 

Support

• Consult Tracking

• Alerts and Reminders

• Role-based Security

• Health Data Dictionary

• Master Patient Index

• Replacement of 

Ancillary Functions of 

Legacy CHCS

• Release 1

-

Pharmacy

• Release 2

-

Laboratory

-

Anatomic Pathology

• Release 3

-

Radiology

Block 1 Block 2 Block 3 Block 4

• Inpatient 

Documentation,  Order 

Entry and Results 

Retrieval

• Occupational Health 

Surveillance

• Release 1

-Dental Charting and 

Documentation

-Spectacle Request 

Transmission System II

• Release 2

-Ad Hoc Query Ability 

2 

-ACPGs

• Encounter 

Documentation

• Order Entry and Results 

Retrieval 

1

• Encounter Coding 

Support

• Consult Tracking

• Alerts and Reminders

• Role-based Security

• Health Data Dictionary

• Master Patient Index

• Replacement of 

Ancillary Functions of 

Legacy CHCS

• Release 1

-

Pharmacy

• Release 2

-

Laboratory

-

Anatomic Pathology

• Release 3

-

Radiology

Block 1 Block 2 Block 3 Block 4


IMPLEMENTATION GUIDE

September 20, 2004
[image: image2.png]



Version 8.0

Foreword

You are about to implement one of the world’s premier electronic health records system – the Composite Health Care System II (CHCS II). CHCS II brings to life the comprehensive, life-long record of care for beneficiaries of the Military Health System (MHS) that was directed by Presidential Executive Order and Congressional mandate. Retrieval of patient information from over 600 MHS treatment facilities around the globe will soon become a reality. Implementing this remarkably advanced system requires leadership presence, support and perseverance. Over time, the electronic health record will fundamentally change many business processes within MHS medical and dental treatment facilities (M/DTFs). The recall of information on previous patient encounters will become nearly instantaneous. Automated coding of encounters will reduce provider labor involved in billing processes, increase collections, and ensure compliance with the Center for Medicare and Medicaid Services billing standards. Soon, the necessity for a paper health record will be diminished.

This Implementation Guide provides a high-level summary of activities each facility’s CHCS II Project Officer will be engaged in prior to and during implementation. This guide was written specifically for MTF Project Officers and their implementation teams by the Clinical Information Technology Program Office (CITPO) Deployment Operations Center. The CITPO, which serves as the program office for CHCS II, established the Deployment Operations Center to provide a central point of contact to assist Service Medical Chief Information Officers (CIOs), their CHCS II deployment teams and MTFs with deployment, training, and activation issues. The Deployment Operations Center staffs a toll-free line (866-837-1924) with automated directory assistance to ensure that any facility with a question or issue can obtain help quickly and easily. Questions can also be addressed to CITPO-OPSCTR@ha.osd.mil. 

This Implementation Guide is just one of the documents that have been created to support you and your implementation team. Additional guidance documents and templates for use in developing your customized, site-specific plans will be provided to you and your implementation team. You also may access these materials online. The Deployment Operations Center maintains an electronic library of all implementation-related documents. (Log on to the CITPO Intranet at www.citpo.ha.osd.mil. Click on the yellow Register bar in the upper right corner of the site to register for access to the Deployment Operations Center content). You may have received a copy of the Commander’s Guide from your facility’s leadership. It outlines CHCS II implementation from a Commander’s perspective. If you have not had the opportunity to review Commander’s Guide, please refer to the electronic copy available online. 

It is our mission to support your throughout this implementation. We look forward to a collaborative working relationship resulting in the successful implementation of CHCS II at your facility. –The CITPO Deployment Operations Center

Prepared By: 

The CITPO Deployment Operations Center

Skyline 2, 5203 Leesburg Pike, Suite 907

Falls Church, Virginia 22041

(703) 284-7400 or (866) 837-1924

CITPO-OPSCTR@ha.osd.mil
41.
Introduction


51.1.
CHCS II System Description


6FIGURE 1: CHCS II DATA FLOW


71.2.
Costs


72.
CHCS II Implementation Roles and Responsibilities


72.1.
Service Representatives


82.2.
CITPO Team


82.2.1.
CITPO Program Manager


82.2.2.
CHCS II Project Officer


82.2.3.
CITPO Director Logistics


82.2.4.
CITPO Director for Systems Implementation


92.2.6.
CITPO Deployment Operations Center


92.2.7.
CHCS II Implementation and Training (I&T) Vendor


92.3.
Tri-Service Infrastructure Management Program Office (TIMPO)


102.3.1.
TIMPO CHCS II Implementation Activities


102.3.2.
TIMPO CHCS II Sustainment Activities


102.4.
Defense Information Systems Agency (DISA)


102.5.
MTF Project Team


102.5.1.
MTF Project Officer


112.5.2.
MTF Clinical Champion


112.5.3.
MTF Facility Training Coordinator


122.5.4.
MTF Systems Administrator(s)


122.5.5.
Client Administrator(s)


132.5.6.
MTF Data Mapping Liaison


132.5.7.
MTF Clinic Representatives


133.
Pre-Implementation Activities


133.1.
Pre-Implementation Coordination


133.2.
Pre-Implementation Conferences


143.3.
Data Mapping


143.3.1.
Data Mapping and Standardization


143.3.2.
Data Mapping Sustainment


153.4.
Site Surveys


153.4.1.
Technical Site Survey Activities (TIMPO and DISA)


16FIGURE 2: COMMUNICATION AND COMPUTING INFRASTRUCTURE


173.5.
Functional Site Survey Activities (CITPO)


183.6.
Communications and Computing Infrastructure Pre-Implementation Requirements


183.6.1.
Community of Interest Last Mile Installation Plan and Schedule


183.6.2.
Site Concurrence Letter


183.6.3.
Ports and Protocols Sign-Off Sheet


193.6.4.
TIMPO LGS Installation Control Document


193.7.
Site Preparation


193.7.1.
Facility Modifications


193.7.2.
Other Communications/Infrastructure Upgrades


203.7.3.
Legacy (CHCS) Preparation Activities


213.8.
Identify Clinic Activation Sequence


213.9.
Site-Specific Implementation and Training Plan (SSITP)


213.10.
Facility-Level Planning Meetings


223.11.
Pre-Implementation Meetings


224.
Implementation and Training Activities


224.1.
Procurement of Hardware (Servers and EUDs)


234.1.1.
Delivery


234.1.2.
Receipt


234.1.3.
Hardware Storage Requirements


234.1.4.
Hardware Configuration Space Requirements


234.1.5.
Disposal of Packaging Materials


235.
Hardware and Software Installation and Testing


235.1.
Server Installation and Integration Testing


245.1.1.
Data Mapping Verification


255.1.2.
25-Month Data Pull


255.1.3.
End User Device Installation


255.1.4.
Network Readiness Assessment


266.
Training Concept of Operations


266.1.
Preparation for CHCS II Training


266.1.1.
Training Rooms


266.1.2.
Training Hardware


276.1.3.
CHCS Basic Training


276.1.4.
Basic Computer Skills Training


276.2.
Creation of CHCS II User Accounts


276.3.
CHCS II Training


276.3.1.
End User Training


276.3.2.
Training Methodologies


286.3.3.
Systems Administration Training


286.3.4.
Client Administrator Training


286.4.
Implementation Assistance


297.
Operations and Sustainment Activities


297.1.
Sustainment Training


297.2.
Notification of CHCS II Downtimes or System Degradation


307.2.
MHS Help Desk/Tier Support


318.
In Closing


32APPENDIX A: Drivers for Development of CHCS II


34APPENDIX B: Points of Contact


35APPENDIX C: Companion Documents




1. Introduction

CHCS II is a single, standard solution for managing beneficiary medical and dental health care in all DoD treatment facilities. CHCS II provides real-time, around-the-clock access to legible medical and dental records, facilitating the delivery of timely and appropriate treatment. CHCS II will be used in the delivery of health care in all Army, Navy and Air Force fixed medical facilities and in deployed medical facilitates, ensuring that all active duty and retired Service members and their family members will have a comprehensive, legible, secure medical record that is standardized across the Services. 

CHCS II enhances the information workflow of MHS health care providers and supports collaborative care by tracking all health care activities. All data is documented electronically, from the patient check-in to the completion of the health care encounter. An electronically accessible health record is generated and maintained by CHCS II, allowing for quality measurement and utilization management. At the close of the encounter, coding is accomplished electronically as a byproduct of documenting the clinical care given to the patient.

CHCS II establishes the means to gather health data, assess medical and dental history, and determine the health status of an individual or a population. Furthermore, the system provides data for the health care providers to make informed, definitive decisions on health care of members of the Armed Forces assigned worldwide, as well as those members deployed as part of contingency operations at home or abroad. The system provides the capability to document present health care and to retrieve the life long record of medical and dental care as well as data on immunization status. 

The system will include documented records of all health care services rendered, including medical examinations, individual encounters, and episodes of care; changes in individual health status; pre-deployment and post-deployment medical exams and assessments, including dental and mental health; and proactive demand management for health care services. Additionally, the CHCS II will be the source for data on an individual’s exposure to different environmental and occupational hazards. These electronic records will allow for surveillance, which will help prevent illness and identify illnesses that occur. 

CHCS II accomplishes four fundamental goals: 

1) Documentation of outpatient encounter for all MHS beneficiaries at any treatment facility: 

· Graphical user interface designed by military providers

· Structured document maintains integrity of patient data and standardization

· Templates simplify workflow

2) Access to ancillary data (Radiology/Pharmacy/Lab): 

· Currently presented through a graphical user interface

· Future blocks of CHCS II will integrate new commercial-off-the-shelf products, replacing current functionality with more advanced capabilities. 

3) Longitudinal storage of all patient data for the enterprise in a central location:

· Provides 24x7 access to complete and legible health and dental patient records

· Enables population health reporting

4) Provides clinical functionality for the Theater Medical Information Program (TMIP)

· Use of same basic system in garrison and theater supports uniformity of records and the records requirement for available health care data at the point of care (available in future blocks)

· There are many drivers for the development and fielding of CHCS II. A complete description of these drivers is available at Appendix A.
1.1. CHCS II System Description

CHCS II builds on to the capabilities of existing systems, subsuming their functionality over time, while adding new functions to meet mission requirements. With the Block 1, the CHCS II initially provides support capabilities in the ambulatory settings while the mature system extends those capabilities into the inpatient arena.

The first blocks of CHCS II will be dependent upon Legacy CHCS for laboratory, radiology, and pharmacy order entry and results retrieval. 

Future blocks of the CHCS II will integrate state of the art laboratory, radiology, and pharmacy order entry systems, enabling the replacement of the functionality of legacy CHCS within the CHCS II. The ultimate goal is to migrate all legacy CHCS functionality, as well as functionality of other clinical applications, into the CHCS II. Under the principles of evolutionary acquisition, the system is designed to accommodate changes and to facilitate the integration of future systems and technology as they evolve. 

CHCS II support the following capabilities: 

Table 1:  CHCS II Capabilities

[image: image1.jpg]QHC}‘S/\ / %/

EEEEEEEEEEEEEEEEEEEEEEEEEEE




A commercial Clinical Patient Record (CPR) product – the 3M Care Innovative Suite – is the basis of CHCS II. This product provides three core elements of CHCS II, including the Health Data Dictionary, the Clinical Data Repository, and the Master Patient Index. 

The Health Data Dictionary (HDD) is the foundation for the CPR. It functions as a lexicon, cross-referencing all data concepts with other internationally accepted coding schemata to eliminate vocabulary and synonym problems, supports data exchange between independent computer programs, and supports the encoding of data to remove the ambiguities that may exist in natural language. 

The Clinical Data Repository (CDR) integrates patient data into a central database of individual lifetime records for access and clinical analysis, provides efficient, centralized access to a patient’s lifetime medical record at the point of care, and preserves investment in legacy systems by exchanging data through open system architecture and standards compliance. 

The Master Patient Index (MPI) links an individual’s health information across all MHS points of care regardless of geographic location. This includes matching the patient’s data from multiple CHCS host sites. 
[image: image3.jpg]CHCS II (new data)

Information Model
Clinical Data Repository

“Lexicon”
Health Data Dictionary

Cl al Event
Patient
Event
Date/Time
Event Status
e e Observation
FE Huuml Sty
Semantic link

Clinically relevant data
semapped fo Jessoon (sandardiveilleodid -




FIGURE 1: CHCS II DATA FLOW
1.2. Costs

Costs for the design, development, and testing of CHCS II software are centrally funded at the MHS level. The application’s implementation and initial training at treatment facilities worldwide also are centrally funded. End user devices, servers, and other associated hardware and software are provided by the central program. The hardware and software will be upgraded on a periodic basis. 

The treatment facility will incur operating costs for paper, toner, power, heating, ventilation, and air conditioning. Additional costs may arise on a site-to-site basis. Such costs may be associated with: 

· New construction (i.e. communication closets)

· Initial supplies, furniture, etc. (i.e. supporting placement of end user devices)

· Communications Local Area Network support and/or upgrade (i.e. beyond that required to specifically support the clinical encounter)

· Modifications of local business and clinical processes to maximize the capabilities of the technology

· Sustainment training

2. CHCS II Implementation Roles and Responsibilities

The implementation of CHCS II requires the dedicated effort of many organizations. These organizations include, but are not limited to, MTF implementation teams, CITPO, the Tri-Service Infrastructure Management Program Office (TIMPO), Service Representatives, support and integration contractors, and CHCS II users at the MTF level. The roles of each of these organizations are addressed in the following paragraphs (2.1- 2.5).

2.1. Service Representatives

Each Service has a Medical CIO responsible for oversight of information management and communications operations. Each Medical CIO has designated a representative to assist and coordinate Service-specific issues and facilitate CHCS II implementation at the treatment facilities. These representatives serve as team leaders for the Service-specific implementation team, and act as a primary interface between CITPO, TIMPO, military departments, and the treatment facilities. 

2.2. CITPO Team

The CITPO interfaces with the Service Representatives and with the implementation team at each site. The CITPO team includes: 
2.2.1. CITPO Program Manager 

In his role as the senior acquisition officer for MHS clinical information technology systems, the CITPO Program Manager provides oversight and guidance for the CHCS II program.  He is accountable to the MHS Chief Information Officer (CIO), to the JMIS Program Executive Officer (PEO), and to the Service Surgeons General for delivery of CHCS II within cost, on schedule, and with performance that meets or exceeds thresholds defined in the CHCS II Operational Requirements Document (ORD).  In this role, the CITPO Program Manager serves as the primary integrator across the CITPO development, testing, deployment, and sustainment communities and across other MHS and DoD government offices and agencies involved in the successful delivery of CHCS II.

2.2.2. CHCS II Project Officer

The CHCS II Project Officer is responsible for the overall design, development, testing, and performance of CHCS II. He or she coordinates directly with the Service Representatives and their staff. The CHCS II Project Officer also is responsible for managing Tier 3 vendor support. Tier 3 support is required when the MHS Help Desk is unable to resolve a trouble ticket or if a request for software enhancement or capability is generated. (See section 7.2. for phone numbers and additional information on the MHS Help Desk.)
2.2.3. CITPO Director Logistics 
The CITPO Director of Logistics executes a support program that meets operational support performance requirements and sustainment of systems in the most cost effective manner for the life cycle of the system.  The Director of Logistics manages the acquisition and procurement of all sustainment activities for the CITPO.  This includes, but is not limited to, site operations, hardware maintenance, software maintenance, mid-life hardware upgrades, and three-tiered technical support.  Provides guidance and oversight for the CHCS, CHCS II Project Officers and their respective teams—a total of approximately 100 government and contractor personnel.
2.2.4. CITPO Director for Systems Implementation 

The CITPO Director of Systems Implementation is responsible for the overall implementation and training of CITPO systems. As the CHCS II Implementation and Training Task Manager, he or she provides the services necessary to introduce and fully activate MHS clinical applications in health care facilities. The scope of activities includes implementation planning, functional site surveys, demonstrations, training, and user implementation assistance support.  Additionally, he or she is fiscally responsible for the CHCS II implementation and training budget. 

2.2.5. CITPO Deputy Directors for Systems Implementation 

The CITPO Deputy Directors for Systems Implementation each support one Service and serve as the primary CITPO point of contact for fielding CHCS II to their respective Service military treatment facilities (MTF).  Working out of the CITPO Deployment Operations Center, they coordinate and manage pre-implementation activities, implementation and training activities, and transition to sustainment activities for Service MTFs.   The Deputy Directors coordinate implementation support with CITPO contractor personnel, representatives from TIMPO and DISA, representatives of the Services’ CHCSII Program Offices, Military Treatment Facility (MTF) deployment teams, and multiple commercial vendors.  

2.2.6. CITPO Deployment Operations Center
The CITPO Director for Implementation is dual-hatted as the Director of the CITPO Deployment Operations Center (DOC).  The DOC, staffed with military and civilian representatives from each of the Services and key organizations, serves as the primary integrator for all activities required to implement CHCS II in treatment facilities worldwide.  The DOC works integrated schedules with each Service, conducts pre-implementation meetings with each MTF receiving CHCS II, and provides centralized points of contact for assistance with all deployment issues.  Through the DOC, prompt resolution of infrastructure, application, or training issues is achieved through direct coordination with responsible organizations.   
2.2.7. CHCS II Implementation and Training (I&T) Vendor

The CITPO Director for Systems Implementation is the government task manager for the CHCS II I&T contract. In coordination with the CITPO Deputy Directors for Systems Implementation, the vendor interfaces with the Service Representatives for all CHCS II Implementation and Training activities. The I&T vendor is responsible for, but not limited to, the following tasks: 

· Pre-implementation planning assistance

· Functional site surveys
· Initial CHCS II client software installation activities

· Initial training and implementation assistance (over-the-shoulder)

· Constant 2-way communications with and through the CITPO Deployment Operations Center and the Services’ planning and execution teams
2.3. Tri-Service Infrastructure Management Program Office (TIMPO)

The TIMPO provides a broad spectrum of information technology services in the areas of implementation, sustainment, and outsourcing for all MHS automated information technology systems to include CHCS II. 

2.3.1. TIMPO CHCS II Implementation Activities

In support of CHCS II, TIMPO: (1) conducts the technical surveys to determine Wide Area Network, Campus Area Network and Local Area Network  requirements; (2) deploys the network protection and encryption solution; (3) deploys the Legacy Gateway Server (LGS) to include implementation of the ports and protocols; (4) procures and deploys the End User Devices (EUDs); and (5) conducts network readiness assessments to ensure the communications infrastructure will support the CHCS II deployment.
2.3.2. TIMPO CHCS II Sustainment Activities

TIMPO sustainment activities in support of CHCS II include application performance monitoring, network monitoring, and EUD life cycle management. 

2.4. Defense Information Systems Agency (DISA)

DISA is the DoD’s preferred provider for Net-centric computing support. In support of these DoD objectives, DISA has developed a robust group of System Management Centers (SMC) that are located in secure facilities on military installations to ensure exceptional physical security of CHCS II records.

In addition to DISA’s secure computing centers, DISA manages a secure DoD communication network known as the Defense Information System Network (DISN).  In support of CHCS II, the DISA is continually expanding the DISN Wide Area Network (WAN) to ensure that each of the 142 major CHCS II sites have redundant WAN circuits to support communications with the CHCS II Clinical Data Repository (CDR) in Montgomery, Alabama.

Even though the DISN is the network designed principally for the exclusive use of the DoD, DISA also ensures that all DISN circuits between the CDR and each legacy CHCS host site is secured via state of the art Virtual Private Network (VPN).  Full VPN coverage of the portion of the DISN that the MHS utilizes provides a high-level encryption that protects sensitive medical information and helps to ensure MHS compliance with the Health Insurance Portability and Accountability Act (HIPAA). 

DISA services are procured by the CITPO through the TIMPO.

2.5. MTF Project Team

Facility leadership and commitment are vital to the success of this endeavor. The appointment of experienced, empowered, and motivated personnel to serve in the key leadership positions is highly recommended. The team should include medical and dental (for sites Deploying Block 2) staff and satellite site representatives, outlined in sections 2.5.1. through 2.5.7.

2.5.1. MTF Project Officer

The MTF Project Officer’s primary duties are the management and oversight of all CHCS II related activities at the facility and the provision of direction to the MTF’s Project Team. This individual is the Commander’s personal representative for this project and must have sufficient experience, seniority, and commitment to interact with the MTF Command groups, their Service Implementation Office, the CITPO and TIMPO staff, and to successfully orchestrate myriad tasks at the local level. The MTF Project Officer is the primary point of contact of the Service Representative for all matters regarding CHCS II deployment at the site. 

The person selected for the role of Project Officer should posses an in-depth knowledge of the facility’s clinical operations. The Project Officer leads the site’s project team and requires the authority to coordinate the selection of the local implementation team members, to conduct local project team meetings, and to participate in meetings with the CITPO. 

2.5.2. MTF Clinical Champion

Because of the clinical focus of CHCS II, the CITPO recommends that a physician or dentist (for Block 2 sites) with strong leadership abilities be identified as the MTF Clinical Champion to work with the MTF Project Officer. Next to the Commander and Project Officer, the CHCS II Clinical Champion may prove to be the most important member of the MTF Project Team. Health care providers will naturally look to a fellow physician for support, guidance, and feedback on CHCS II during deployment. A senior, well-respected physician who is knowledgeable of CHCS II and its potential to enhance health care delivery can provide the clinical perspective and leadership needed to ensure provider adaptation. The clinical champion also provides valuable insight into template management and mechanisms to optimize integration of CHCS II into the clinical environment. 

2.5.3. MTF Facility Training Coordinator

The MTF Facility Training Coordinator works with the CITPO Logistics team, the Implementation and Training vendor, local staff, and remote clinics to ensure that users are scheduled for and complete initial training in accordance with the training resources programmed for the MTF. It is imperative that the MTF Facility Training Coordinator, in coordination with the CITPO Logistics and their Service’s CHCS II training point of contact (POC) translate the training model into an efficient site-specific execution product. Each site has a pre-determined number of instructor and implementation assistant hours allocated based upon each Service’s specific training strategy. Exceeding these training resource hours could jeopardize the resources available to subsequent training sites within their respective Service. 

Activation is generally defined as when the first trained user begins using CHCS II. Activities include identifying users for training, scheduling training rooms, coordinating closely with clinical representatives to schedule users into training slots, disseminating the training schedule throughout the facility, ensuring user are instructed with role-appropriate CHCS training as a pre-requisite to CHCS II training, and assisting the Implementation and Training personnel in preparing sites for activities. For CHCS users who have used only VT 100 terminals, training on Windows and use of the mouse is strongly recommended as a pre-requisite to CHCS II training.

Classes need to be filled to capacity with little or no downtime between classes in order to assure that the MTF user training is completed within the scheduled time frame. The MTF Facility Training Coordinator must monitor no-shows and ensure that training schedules are communicated to all clinics well in advance of their designated training dates. He or she may also need to assist the I&T vendor with coordination of over-the-shoulder training once use of CHCS II begins at the clinics. 

The MTF Facility Training Coordinator works with the education and training staff at the facility to establish a program of ongoing/sustainment training after implementation is completed. (See section 6.3.5. for more on the Train the Trainer program designed to support development of a sustainment training cadre.) 

2.5.4. MTF Systems Administrator(s)

CHCS II introduces client/server architecture to the MHS suite of clinical systems. While DISA provides operations and support for CHCS II servers physically located at host site MTFs, there are some touch labor requirements. For CHCS host sites, the system administrator requirements include this touch labor along with CHCS II user account creation responsibilities and coordination with CITPO, TIMPO, Services, and contractors during installation activities. 

Overall responsibilities for host site system administrators include the following: 

· Daily morning checks on CHCS II Legacy Gateway Server (LGS)

· Problem resolution with DISA along with trouble ticket documentation

· Provide network access and computer room access

· Provide internet protocol addresses

· Ghost LGS prior to any new CHCS II software release

· Follow standard reporting procedures for scheduled and unscheduled downtimes

· Create CHCS II user accounts for host facility

· Assist with CHCS II user account management activities for satellite facilities
2.5.5. Client Administrator(s)

The role of the MTF Client Administrator(s) may vary from site to site. Some MTFs may dual hat this role with Tier 0 Help Desk personnel or with other systems personnel responsibilities. Overall responsibilities for the client administrator include the following: 

· Ensures installed equipment is managed in accordance with DoD and Service directives

· Troubleshoot workstation-related problems

· Assist with auto-update of CHCS II (according to MTF plan for release management procedures)


2.5.6. MTF Data Mapping Liaison

The MTF Data mapping Liaison assists with data standardization and mapping activities.  Initial activities include reconciling treatment facility data as it is mapped to the CHCS II Health Data Dictionary, coordinating throughout the facility to identify personnel with appropriate expertise, and assisting with facility data clean up and conversion activities.  During the sustainment phase, the data mapping liaison may continue to be contacted by the data mapping vendor should questions arise pertaining to data requirements for the MTF.
2.5.7. MTF Clinic Representatives
MTF Clinic Representatives assist with obtaining access to the clinics for installing hardware and software, work with the Facility Training Coordinator to identify and schedule training for staff, provide regular feedback to the facility’s Project Officer, and coordinate implementation activities between clinic personnel and the facility’s Project Team. Each clinic should have its own representative to ensure that clinic users are kept well informed of CHCS II activities.

It is strongly recommended that a knowledgeable Clinic Representatives accompany the I&T vendor during functional site surveys to identify the “as-is” clinic workflow (see paragraph 3.4.).   
3. Pre-Implementation Activities

During the pre-implementation phase (the period preceding the MTF’s first CHCS II training day or “T-Day”), the MTF Project Team collaborates with the project management entities addressed above (see paragraphs 2.2. through 2.5.) to prepare the site to receive CHCS II. Initial contact with the facility generally begins approximately 6 to 12 months prior to the start of CHCS II training. 

3.1. Pre-Implementation Coordination

The Service Representatives coordinate with the CHCS II MTF Project Team to arrange the following on-site visits: 

· Technical site surveys

· Functional site surveys

· Briefings and orientations

· Delivery and installation of hardware and software

3.2. Pre-Implementation Conferences

The CITPO will host and facilitate a pre-implementation conference for MTFs approximately six to nine months prior to training. The two-day conference provides one day of structured presentations and a demonstration of the application followed by half-day of Service-specific break out sessions. The conferences are typically held in the Washington, DC metro area and require travel and time away from the MTF to ensure full participation. Each site will receive notification for the Conference through their respective Service CIO Representatives approximately 90 days prior to the conference date. Notifications include travel guidelines, registration forms, agenda, and other pertinent materials. Participant evaluations from previous conferences indicate that attendance at these conferences is especially helpful to ensure successful deployment of CHCS II at their MTFs. 

3.3. Data Mapping 

As part of CHCS II pre-deployment activities, the CITPO is required to map specified metadata between CHCS host sites and the CHCS II. The CHCS host site’s data is standardized as it is mapped to the CHCS II Healthcare Data Dictionary (HDD). Data mapping activities include the initial mapping and standardization, sustainment activities and data mapping verification following CHCS II server installation.

3.3.1. Data Mapping and Standardization

CHCS II Clinical Data Standardization (data mapping) is comprised of data extraction of CHCS site images, data preparation, data cleansing, data mapping and validation through the treatment facility’s Subject Matter Experts. The data-mapping contractor coordinates this through the Service Representative. It is critical for the facility to participate in this activity. Data is mapped completely and then verified as accurate.  Data standardization and mapping was completed for all MTFs in mid-Fiscal Year 2004.  
3.3.2. Data Mapping Sustainment

Data Mapping Sustainment is the process for managing data changes to CHCS that occur after initial data standardization and mapping these changes to CHCS II. The two systems must be synchronized as data items are added or modified in CHCS. The process for each treatment facility began immediately following the completion of initial data mapping verification. It includes the daily programmatic extraction of changes made in certain CHCS data files (see below). The data mapping vendor sustains the data mapping process to ensure the continuing high levels of data quality supported by the CHCS II HDD.

The following files are maintained: 

· Laboratory

· Pharmacy (including drug formulary)
· Radiology

· Microbiology

· Anatomical Pathology

· Administrative files (i.e., command interest, insurance, patient category, etc.)

· Standard coding files
Subject matter experts (SMEs) for laboratory, radiology, pharmacy, insurance, admissions, dispositions, and transfers are needed at times to resolve questions regarding modifications to site data. SMEs should be designated to facilitate question resolution. 

Data mapping verification post server installation is further addressed in paragraph 5.1.1.
3.4. Site Surveys

The TIMPO, DISA and the CHCS II Implementation and Training vendor,  in coordination with the appropriate Service Representatives, conduct the technical and functional site surveys at each facility approximately six to nine months prior to scheduled activation. The technical survey takes approximately five working days. The functional site survey takes between five to fifteen working days depending on the size of the facility and the number of satellites. 

The MTF Project Officer is a key part of each site survey team. This individual assists the TIMPO, CITPO, and DISA Representatives to ensure each site is ready for these surveys, provides the necessary access for these individuals and coordinates visits with other site personnel, such as civil engineers, the CHCS system administrator, local area network maintenance personnel, clinic representatives, and base communications personnel. 

3.4.1. Technical Site Survey Activities (TIMPO and DISA)

The Technical Site Survey focuses on Community of Interest network, Last Mile network connectivity and the host site’s computer room.   It is conducted by TIMPO and DISA approximately 210 days prior to training start.  In support of this survey, TIMPO hosts a pre-site survey teleconference (approximately 14 days prior to initiating the site survey) to review the site specific information package (developed and provided by TIMPO).  Required participants include representatives from the MTF, Network Control Center, the Directorate of Information Management and the Services).  
3.4.1.1. Community of Interest (COI) Network

DISA is responsible for implementing a quality of service wide area network transport solution which is optimized and designed for real-time, transaction processing of the CHCS II client-server application. The Community of Interest is a redundant, diversely routed asynchronous transfer mode permanent virtual circuit for larger facilities and dedicated point-to-point circuits (e.g. T1s) for smaller facilities such as clinics. DISA surveys locations on the base, post, camp, or station where the wide area network circuit terminates (service delivery points). Information gathered during the survey supports the development of a detailed Community of Interest design. 

3.4.1.2. Last Mile

TIMPO surveys the communications connectivity from the defined Community of Interest Service Delivery Point (SDP) to the facility’s perimeter. As illustrated in Figure 2 below, the “Last Mile” generally refers to the communications extension from the SDP to the facility’s exterior router for medical buildings located on a military installation or campus. Off-base facilities, such as those on a stand-alone medical campus also may have a Last Mile from the long-haul demarcation point to the facility’s exterior router at each building. Information gathered during the survey supports the development of a detailed Last Mile design. 
3.4.1.3. MTF Host Computer Room
TIMPO assesses: 

· Adequacy of floor space and the location for the legacy gateway server and rack
· Adequacy of electrical, environmental control, security, and communications systems

· The physical connections of wiring and circuitry

At the end of the technical survey, the site survey team provides an out-brief summarizing the site survey results and findings (a copy of the out-brief is delivered to the facility on the last day of the survey).  The TIMPO / DISA team will identify deployment critical issues and long lead items (e.g., problems with rack space and power, significant environmental concerns, lack of connectivity or fiber with select facilities or between the DISA Service Delivery Point and the facility) in the out-brief and follow-on design documents as they are identified. 

FIGURE 2: COMMUNICATION AND COMPUTING INFRASTRUCTURE

[image: image4.emf]Off-Base MTF

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

On-Base MTF

Security

Suite

LAN

Base/Post/Camp

Network (LAN)

Security

Suite

The “Last Mile” provides

connectivity from the

MHS COI SDP to the

MTF perimeter.

S

D

P

Montgomery DECC

San Antonio DECC

CDR FEPs

‘

Logical CDR Service’

S

D

P

COI SDP

S

D

P

COI SDP

R&D

MHS COI

COI SDP

Last Mile

Off-Base MTF

Security

Suite

LAN

Off-Base MTF

Security

Suite

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

On-Base MTF

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

Security

Suite

LAN

On-Base MTF

Security

Suite

Security

Suite

LAN

Base/Post/Camp

Network (LAN)

Security

Suite

Base/Post/Camp

Network (LAN)

Security

Suite

Base/Post/Camp

Network (LAN)

Security

Suite

The “Last Mile” provides

connectivity from the

MHS COI SDP to the

MTF perimeter.

The “Last Mile” provides

connectivity from the

MHS COI SDP to the

MTF perimeter.

S

D

P

Montgomery DECC

San Antonio DECC

CDR FEPs

‘

Logical CDR Service’

S

D

P

COI SDP

S

D

P

COI SDP

R&D

MHS COI

COI SDP

S

D

P

S

D

P

Montgomery DECC

San Antonio DECC

CDR FEPs

‘

Logical CDR Service’

S

D

P

S

D

P

COI SDP

S

D

P

S

D

P

COI SDP

R&D

MHS COI

COI SDP

Last Mile

DISA Responsibility

TIMPO/Service Responsibility

Off-Base MTF

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

On-Base MTF

Security

Suite

LAN

Base/Post/Camp

Network (LAN)

Security

Suite

The “Last Mile” provides

connectivity from the

MHS COI SDP to the

MTF perimeter.

S

D

P

Montgomery DECC

San Antonio DECC

CDR FEPs

‘

Logical CDR Service’

S

D

P

COI SDP

S

D

P

COI SDP

R&D

MHS COI

COI SDP

Last Mile

Off-Base MTF

Security

Suite

LAN

Off-Base MTF

Security

Suite

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

On-Base MTF

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

LAN

SDP

MTF Bldg

Security

Suite

Security

Suite

LAN

On-Base MTF

Security

Suite

Security

Suite

LAN

Base/Post/Camp

Network (LAN)

Security

Suite

Base/Post/Camp

Network (LAN)

Security

Suite

Base/Post/Camp

Network (LAN)

Security

Suite

The “Last Mile” provides

connectivity from the

MHS COI SDP to the

MTF perimeter.

The “Last Mile” provides

connectivity from the

MHS COI SDP to the

MTF perimeter.

S

D

P

Montgomery DECC

San Antonio DECC

CDR FEPs

‘

Logical CDR Service’

S

D

P

COI SDP

S

D

P

COI SDP

R&D

MHS COI

COI SDP

S

D

P

S

D

P

Montgomery DECC

San Antonio DECC

CDR FEPs

‘

Logical CDR Service’

S

D

P

S

D

P

COI SDP

S

D

P

S

D

P

COI SDP

R&D

MHS COI

COI SDP

Last Mile

DISA Responsibility

TIMPO/Service Responsibility


3.5. Functional Site Survey Activities (CITPO)


The functional site survey results in three primary products that are extremely important to the successful implementation of CHCS II at your facility – numbers, types, and location of End User Devices (EUDs); numbers and types of users requiring training; and a work process analysis  (referred to as “process maps” in the Best Practices approach) for your facility.

In order to prepare for the survey, a teleconference is conducted with the Service Representative, the MTF Project Team, the Implementation and Training vendor and a representative of CITPO. The purpose of the teleconference is to introduce team members, discuss the necessary logistics for base and clinic access, outline survey team objectives, identify who is responsible for populating the Functional Pre-Site Survey Questionnaire, and schedule review. 

The facility is responsible for providing an escort to the Site Survey Team. It is recommended that this person be knowledgeable of clinic operations and be able to discuss clinic workflow. It is recommended that the facility schedule specific times for a Site Survey Team to be at each clinic. The Site Survey Team requires approximately an hour per clinic, depending on size. 

3.5.1. End User Device Requirements

The Functional Site Survey uses the Service-endorsed Device Placement Criteria to identify end user devices needing replacement and to determine if existing end user devices and printers meet technical specifications for CHCS II.   In addition, the survey identifies any additional local area network drops required to ensure proper placement of these devices. 

Using the data collected during the functional site survey, the MTF and Service Representatives must identify the total number of end user devices required per Parent DMIS ID Site approximately 180 days prior to the activation date. 


3.5.2. MTF Training Requirements
The functional site survey team will require the assistance of MTF personnel to identify and validate the number of users requiring training by skill set (providers, nurses, technicians, clerks, records review personnel).  The team will inquire if there are any VA providers who provide care to both DoD and VA patients in your MTF. It is important for the site to identify these providers so that they will be included in the total numbers of users to be trained on CHCS II. 

Additionally numbers and types of training facilities are surveyed to ensure the training rooms can support the training requirements for CHCS II training at the MTF.  


3.5.3. MTF Work Process Analysis (Clinic Process Maps)


In parallel with verifying training and EUD requirements, the site survey team will conduct a work process analysis, documenting the clinical process flow within each MTF/clinic. The surveyors will track the movement of a patient through all activities during a typical visit to a clinic and will be used to customize curricula for the clinic personnel associated with each task within the workflow.  A comparison of site-specific process flows will be compared to the generic CHCS II process flow.  “Touch points” will be identified noting where CHCS II functionality can be used to help enhance the business flow of the clinic.  CHCS II training will be customized to address these touch points.
At the conclusion of the survey, an out-brief is provided to the MTF Project Team and a draft or an interim site survey report of key findings is left with the facility. The Implementation and Training Vendor delivers a site survey report to the CITPO within 15 calendar days following survey completion. A copy of this deliverable is also provided to the appropriate Service Representative. CITPO and the Service Representatives have 10 days to provide any report clarification or changes to the Implementation and Training vendor.
3.6. Communications and Computing Infrastructure Pre-Implementation Requirements

The information gathered during the Technical Site Survey is used to develop the Community of Interest Last Mile Installation Plan and Schedule, the Site Concurrence Letter, the Ports and Protocols Sign-off Sheet, and the TIMPO LGS Installation Control Document. 

3.6.1. Community of Interest Last Mile Installation Plan and Schedule

This plan and schedule lists the tasks, sequence of events, dependencies, required downtime, and responsibilities of all parities, for implementation of the approved Last Mile design for each CHCS Host Site, Parent DMIS Site, and related satellites. The Plan references the Ports and Protocols Sign-off Sheet for information relevant to Last Mile routing and security policy implementation to support CHCS II/Community of Interest data flow. The Community of Interest / Last Mile Installation Plan and Schedule is developed in conjunction with the COI and last mile design documents.   These designs are reviewed with Site/Service representatives ~37-40 days after completing the technical site survey.

The CHCS II community of interest circuit is typically installed by the DISA / TIMPO team approximately 100 days prior to training start.  In many cases, TIMPO or DISA will require support from the base and MTF to support VPN ACL and routing changes and service interruption requirements.  Typically, these COI cutover activities (to include VPN installations) are coordinated through the MHS Help Desk and Medical Infrastructure – Configuration Control Board (MI-CCB) processes.
3.6.2. Site Concurrence Letter

The Site Concurrence Letter is an agreement between the Base, Post, or Camp NCC (Network Control Center), the Information Technology Business Center or the Information Management Division, the Service Military Department Representative, DISA, TIMPO (to include its contractors), and the local facility’s CIO, to implement the approved Community of Interest and the Last Mile solution per the implementation plan agreed to by all parties during the design review and last mile negotiations process. 

3.6.3. Ports and Protocols Sign-Off Sheet

The Ports and Protocols Sign-off Sheet documents requirements for Internet Protocol addresses, access lists, and other configuration changes necessary to permit the proper routing and flow of data between local facility networks (CHCS Host Sites, Parent DMIS, and related Satellites) and the CHCS II Host application located at DISA’s SMC Montgomery, Alabama, via the negotiated Last Mile design. The Sign-Off Sheet must be tailored to support changes at all levels along the Last Mile path regardless of the party who controls that element of the infrastructure. 

A Ports and Protocols teleconference is set up 30 days prior to the LGS installation to review the ports and protocols document.  Required participants include representatives from the MTF, Network Control Center, the Directorate of Information Management and the Services).  The ports and protocols document will be revisited throughout the deployment process to ensure that network continues to support the routing of required traffic between each of the facility and DISA.

3.6.4. TIMPO LGS Installation Control Document
The TIMPO LGS Installation Control Document is used to ensure the facility is ready for the installation of its CHCS II servers.  This includes validating ports and Internet Protocol addresses for both CHCS and CHCS II; ensuring e*Ways have been developed/tested; downloading and installing CHCS software (Enosis, transmitter, MObjects), procuring, shipping and configuring servers; and opening ports between the facility and the Clinical Data Repository. 

This checklist is reviewed twice (approximately 21 days and 7 days prior to the server team arrival) to confirm all activities are completed and issues resolved in preparation for installation.   

3.7. Site Preparation

This activity prepares the facility and CHCS for the scheduled installation of CHCS II hardware and software. The site preparation activities, guided by the results of the site surveys, may include both facility modification/upgrades and Communication and Computing Infrastructure upgrades. CHCS preparation activities insure complete and accurate legacy baseline data prior to the loading of CHCS II at each MTF host site. 

The MTF Project Officer must coordinate site preparation efforts very closely. The site deliverables provide the basic hardware and software Bills of Materials, the hardware footprint, standard server rack configuration, hardware power requirements, and an estimated timeline. The MTF Project Officer can help expedite the process by establishing lines of communication and effective working relationships with base communications personnel, base facilities managers, local contractors, and suppliers, as required. 

3.7.1. Facility Modifications

The facility’s Project Officer is responsible for ensuring completion of any facility modifications that may be required prior to hardware installation. Expected completion date is one month prior to server installation. 

Typical site preparation may include wiring the computer room and/or facilities with additional electrical power outlets, installing or removing walls, reconfiguring environmental control systems, and reconfiguring/relocating existing computer and communications equipment. 

3.7.2. Other Communications/Infrastructure Upgrades

Local Area Network: Most local area network infrastructure upgrades are completed well before implementation of CHCS II. The TIMPO or a designated Services Representative executes the local area network upgrades as detailed by the Services, within the Information Management Proponent Committee’s guidance. 

Many activities require base-level assistance and approval. It is the site’s responsibility to obtain that approval and cooperation. These activities include ordering the required materials, installing communications equipment, and testing the networks as appropriate to ensure the upgrade is functioning properly. The TIMPO or the designated representative ensures that facility’s satellites and outlying clinics have the required infrastructure in place. 

Network Protection: At a minimum all CHCS II data is encrypted while in transit. A NetScreen virtual private network appliance is used to encrypt data from the facility to the Clinical Data Repository. These applications are put in place prior to connection of the Community of Interest Wide Area Network. 

3.7.3. Legacy (CHCS) Preparation Activities

Lessons learned during CHCS II Operational Test and Evaluation (OT&E) and Limited Deployed phases indicate that every effort must be made to ensure an optimal CHCS baseline prior to the activation of CHCS II at any site. Legacy preparation activities include the following: 

· Elimination of duplicate patient records

· Elimination of duplicate provider files

· Addition of social security number, gender, and date of birth to all user profiles

· Review of all clinic and provider profiles for accuracy of count and non-count appointment types

· Loading of specified change packages prior to the arrival of the server installation team

· Executing an ad hoc report for active clinics for the host and satellite MTFs prior to server installation

· Coordinate with MTF network personnel for workstation IP addresses prior to server installation
These activities are managed by site sustainment personnel in coordination with the SAIC Field Operations Manager. 


3.7.4. Application for DoD Network Access and/or DADS Server Access

Though CHCS II Legacy Gateway Servers (LGS) are physically located at each site, base, camp or station Medical Treatment Facility or Network Control Center, software support and system sustainment of these servers require access to Virtual Private Networks maintained by DISA- Montgomery.  Additionally, DISA uses the Defense Applications Distribution System (DADS) to electronically distribute CHCS II upgrades and new software for the LGSs.  Access to either the LGS or DADS requires submission of a DD Form 2875 for access approval.  Any CHCS II government or contractor systems personnel who monitor the LGS, perform touch labor, create CHCS II user accounts, or download software must apply for access approval.  All functional users require an ADP-II clearance and personnel identified as System Administrators require an ADP-1 clearance.

The application process has been automated and streamlined but still requires approximately four weeks to complete.  Applications should be submitted at least 30 days prior to server installation at your facility.  The process for completing and submitting the DD Form 2875 is attached as part of the Companion Documents at Appendix C.
3.8. Identify Clinic Activation Sequence

Each facility determines the sequence and manner in which clinics will be activated. This includes the clinics at the host facility and all remote facilities. The sequence is identified in coordination with the MTF Project Officer, the Service CIO Representative, and the Implementation and Training vendor. Consideration should be given to bringing clinics up in a manner that supports productivity and access to care requirements for each MTF.  

Once finalized and approved by MTF personnel, the sequence is documented in the Site-Specific Implementation and Training Plan (SSITP). In addition, each facility is required to provide its activation sequence in writing to the Deployment Operations Center approximately 90 days before the CHCS II end user training is slated to occur. 

3.9. Site-Specific Implementation and Training Plan (SSITP)

After completing the functional site surveys, the Implementation and Training vendor provides a Site-Specific Implementation and Training Plan for CHCS II related activities to occur at the facility. An initial draft of the plan will be delivered no later than 60 days prior to activation. The final draft is to be completed no later than 30 days prior to activation. Each site’s SSITP must be approved by the CITPO to assure required resources are available to execute the plan. 

The Implementation and Training vendor works with the MTF Project Officer and the MTF Facility Training Coordinator to populate the plan by addressing: 

· Site preparation activities/schedule 

· Clinic activation sequence/schedule

· EUD requirements, delivery, and installation schedule

· Clinic process maps
· Training requirements and schedule
· Training classroom requirements
· Risks and mitigation strategies
3.10. Facility-Level Planning Meetings

A regularly scheduled facility-level planning meeting is recommended to allow all team members to identify and resolve site-specific issues at the lowest level. Issues may include: training schedules, power requirements, space, hospital policy issues, consideration of “as-is” or “to be” business process changes, and end user device requirements. The meeting should be chaired by the MTF Project Officer and should include facility and clinic implementation team members and other participants as needed. Additional participants could include the hospital administration personnel, data quality personnel, clinicians, other health care providers, medical and dental (for Block 2 sites) technicians, information management personnel, and base communication personnel. Tight coordination across a multidisciplinary team is critical to the successful implementation of CHCS II in each facility. 
3.11. Pre-Implementation Meetings

Pre-Implementation Meetings (PIMs) are held prior to system activation to review implementation and training tasks. Participants include the MTF Project Team Members and Service Representatives. The CITPO Deployment Operations Center hosts Pre-Implementation Meetings at 90 days, 60 days, and 30 days prior to the first training date, using a checklist to monitor progress for all pre-implementation activities and readiness of schedule.   The PIMs help to resolve any issues that could adversely affect the activation schedule. Any problems or issues that arise during these meetings are addressed through the collaborative efforts of the CHCS II Integrated Product Team structure. 

The major topics of discussion for the Pre-Implementation Meetings are: 

· Surveys

· End user devices (installation, testing)
· Circuit network protection

· Server installation and integration testing

· Software installation and testing
· Training schedules, Over-the-shoulder assistance, etc. 
· Transition planning and sustainment activities
The PIM Checklist is attached as part of the Companion Documents at Appendix C.
4. Implementation and Training Activities

This phase encompasses execution of activities outlined in this Implementation Guide and the Site-Specific Implementation and Training Plan. During this phase hardware and software is procured, delivered, installed and tested for systems personnel, facility trainers and end user communities.

4.1. Procurement of Hardware (Servers and EUDs)
The DISA acquires the server hardware and software, while TIMPO and/or the Services acquire and maintain end user devices. The EUD hardware and software is configured by the end user device vendor to ensure compatibility with CHCS II and is shipped to the respective treatment facility site. In the event that your treatment facility wants to use existing workstations, the end user device vendor exercises a contract line item for on-site installation of CHCS II software. 

Site and/or user licenses, if required by the vendors, are provided to the treatment facility when the hardware is fielded. The CITPO, regardless of the procurement source, provides configuration management of CHCS II commercial- and government-off-the-shelf software products. 

Using the data collected during the functional site survey, the MTF and Service Medical CIO Representatives must identify the total number of end user devices required per Parent DMIS ID Site approximately 180 days prior to the activation date.

4.1.1. Delivery
Server hardware arrives at the facility no later than 75 days prior to the specific facility’s activation date. EUDs arrive at the MTF no later than 30 days prior to T-Day.  The treatment facility must identify personnel to be responsible for the receipt and inventory of hardware and software until installation. The treatment facility is responsible for configuring any other software loaded on the end user device. 

4.1.2. Receipt

The MTF Project Officer is responsible for identifying to the CITPO a complete shipping address for the treatment facility and the individual(s) authorized to receive the shipment.  Plans for receipt, property book management and securing the hardware is the responsibility of the MTF Project Officer or his/her designee. The MTF will be asked to sign for the server hardware and to sign a Property Acceptance Sheet for the EUDs. 

The vendor is responsible for installing EUDs and will look to the MTF for guidance and a plan for installing the EUDs in a manner that minimizes disruption to clinic activities. 

4.1.3. Hardware Storage Requirements

Each facility must provide secure storage for end user devices and servers as they arrive from the vendors and before they are installed in the computer room or clinics. The MTF Project Officer or his/her designee is responsible for ensuring that the vendor responsible for server installation and end user device installation have access and may retrieve any or all of these devices from storage on an as-needed basis. 

4.1.4. Hardware Configuration Space Requirements

Each facility must provide a minimum of 250 square feet of space for the installation team to stage and configure end user devices earmarked for clinic installation. 

4.1.5. Disposal of Packaging Materials

Unpacking of end user devices and disposal of packaging materials may be done by the TIMPO and/or the Service end user device vendor, depending on the Service procurement strategy.

5. Hardware and Software Installation and Testing

5.1. Server Installation and Integration Testing

Server installation should start 75 days prior to activation. The hardware will come pre-loaded with base (or core) software such as the operating system, standard software applications and tools, etc. Any software, including CHCS II, which was not pre-loaded, will be loaded at the time hardware is installed. Towards the conclusion of server installation testing, final data mapping verification (DMV) will be conducted. (See paragraph 5.1.1. below.)

The CITPO and TIMPO teams coordinate with the facility’s Project Officer to ensure that: 

· A daily installation schedule is designed to minimize disruption of the treatment facility workflow

· Access to the computer room and facility for installation and diagnostic testing is granted

· All equipment is connected to power sources, communication cables are attached, and connections to other units are carried out as specified in the cabling plans

· Software is loaded and diagnostic tests performed to ensure that the system performs to original equipment manufacturer’s specifications

· System burn-in and diagnostic tests are initiated

· Equipment inventories are updated and provided to CITPO

· System integration tests are conducted

· Non-performance reports are prepared

5.1.1. Data Mapping Verification

Final Data Mapping Verification (DMV) is the testing of all mapped data prior to CHCS II activation. Verification is required for each CHCS Host Facility because specific data is mapped for a specific site. 

Final data mapping verification testing occurs after the CHCS II server is connected and tested. All data elements must be tested after the CHCS II server has been installed to ensure that the concept of the data item and the display are correct in CHCS II. DMV is performed through a combination of automated and manual processes via remote access to the CHCS host sites and CHCS II at SMC-Montgomery by a data mapping verification team under the auspices of the CITPO. The MTF Data Mapping Liaison will be contacted through the appropriate Service Representative to coordinate the following for the Data Mapping Verification Testing Team: 

· On-site resources needed

· Roles and responsibilities

· Set up of CHCS user accounts (to be used exclusively by the team)

· Data mapping sustainment continues during DMV, as discussed in para 3.3.2.

5.1.2. 25-Month Data Pull 

After final data mapping verification is completed, CITPO, in coordination with TIMPO and DISA initiates a data pull from CHCS I at your site to the clinical data repository.  The pull brings over 25 months of historical clinical data for your beneficiary population.  Additionally, this data pull ensures that your providers will have historical information on the patients they see from the first day they use CHCS II. 
As additional sites receive CHCS II and the clinical data warehouse facility (in San Antonio, TX) is populated, facilities will be able to mine data for enterprise-wide populations.  
5.1.3. End User Device Installation

End user device hardware and software is installed 30 to 60 days prior to the start of training activities.  Whenever possible, the CHCS II suite of software will be loaded prior to shipment to the MTF. This activity is dependent up timing for new CHCS II software releases which will sometimes preclude factory install of CHCS II. The CHCS II software suite is intended to include the following: 

· Site-specific image

· KEA 5.10H

· Tivoli executable (site-specific)

· CHCS II

The vendor responsible for EUD installation will look to the MTF for guidance and a plan to install EUDs in a manner that minimizes disruption to clinic activities. For Army and Navy MTFs, TIMPO’s EUD vendor will install EUDs in accordance with device placement requirements identified during the functional site survey. A technical test and a functionality test will be performed if CHCS II software is available at the time the EUDs are installed. 

When timing of software releases preclude “factory load” of CHCS II, the software will be loaded by the I&T vendor and a functionality test performed. 
5.1.4. Network Readiness Assessment

TIMPO will coordinate with site representatives, and provide onsite testing to ensure the infrastructure (from EUD to SMC Montgomery) provides the required levels of performance to support the CHCS II application.  For most sites, two visits are required.  The first visit is conducted in conjunction with EUD testing (approximately 28 days prior to training start).  During this visit, TIMPO representatives will normally deploy a Tivoli Gateway Server that is used for application performance monitoring.  The second visit normally starts 4-5 days before training starts and ends 2-3 days after training start (after verification of successful network performance).
6. Training Concept of Operations

The CITPO is responsible for providing on-site resources to ensure that training is available for all users within the scheduled time frame. The MTF is responsible for ensuring the execution of training within the site’s allocated training resources. 

6.1. Preparation for CHCS II Training

Following the functional site survey, the CHCS II Implementation and Training vendor provides a Site-Specific Implementation and Training Plan delineating training start and end dates for role-based user training, client administration training, and train-the-trainer training. The CITPO team, the Service CIO Representative, and the I&T vendor review this plan with the MTF Training Coordinator and address any discrepancies as required. 

The MTF Training Coordinator ensures the training facilities are ready for training classes. Once approved, the Coordinator disseminates the approved training plan and schedule throughout the facility. The Coordinator works with the clinic representatives to ensure that the provider’s schedules are blocked and the providers are booked for training at least 45 to 60 days prior to each provider’s training start date.
Consideration should also be given to the order in which personnel within a clinic will be trained.  Documentation of a clinical encounter supports a team concept for interaction with each patient.  CHCS II clinical encounter documentation begins with patient check-in, proceeds through initial screening and vital signs, and ends with provider documentation and completion of the encounter.  For optimum utilization of CHCS II as a clinical enhancement tool, provider training should be synchronized with that of his or her support staff.  In this manner, providers coming out of training and beginning use of CHCS II will have a team of staff trained to initiate their respective portions of the clinical encounter.

Some MTFs have found it beneficial to train clinic champions and/or clinic leaders early in the training schedule.  By so doing, these individuals are in a position to provide positive guidance and assistance to CHCS II users in their respective clinics.  

6.1.1. Training Rooms

Each CHCS II Training Site must have a minimum of two dedicated training rooms with desks, chairs and electrical power to accommodate at least 10 students and 1 instructor. Some extra-large and large facilities may require additional classrooms depending upon the MTF’s specific training model. 

6.1.2. Training Hardware

Training for CHCS II is conducted on laptop computers configured with the CHCS II Implementation Training Tool. (The training laptops do not remain at the facility following implementation.)

6.1.3. CHCS Basic Training

The CHCS II training curriculum assumes that users are fully trained in appropriate CHCS modules. The Facility Training Coordinator is responsible for ensuring that CHCS training is provided for those requiring it prior to CHCS II training. 

6.1.4. Basic Computer Skills Training

CHCS II uses a familiar graphical interface. The training curriculum assumes students have basic computer skills, including the ability to use MS Windows, drop-down menus, a mouse, and a keyboard. Basic computer skills training and CHCS legacy training are the responsibility of the MTF. 
6.2. Creation of CHCS II User Accounts

New CHCS II software functionality will allow both Host and Satellite Sites to create and manage their own user accounts for CHCS II as they currently do for CHCS I.  The process for creating CHCS II user accounts has been redesigned to use the CHCS I user account as a basis for account creation.  MTFs are reminded to refer to Legacy Preparation requirements (paragraph 3.7.3.) concerning the need to add user information into the gender, SSN, date of birth fields.  These fields are used to verify user information and must be filled in to successfully create user accounts.  Guidance on creating user accounts is attached as part of the Companion Documents at Appendix C. 

6.3. CHCS II Training

The CITPO uses a combination of training methodologies to familiarize users with CHCS II and to help them integrate the system’s use into their clinic work flow. Training duration varies by class type. 

6.3.1. End User Training

CITPO is responsible for the delivery of initial End User Training. The training strategy incorporates adult-learning approaches and personalized hands-on training.  Training duration is based on the user’s job responsibilities and professional background and extends into a 2-4 week period of On-The-Job training (OJT).  OJT, which includes personalized over-the-shoulder training and coaching, enables role-based training to be hands-on and specific to a particular focus.
6.3.2. Training Methodologies


The CITPO I&T vendor provides role-based training for providers, nurses, support staff, clerks, and immunization staff, using a combination of training methodologies.  These methodologies include group discussions and exercises, case studies for scenario-based training, and demonstrations and simulations.  Training materials include a computer-based training product, a training video, and a web-based training tool. 
6.3.3. Systems Administration Training

While DISA holds the primary responsibility for operations and sustainment of CHCS II servers, training is conducted on-site for System Administrator personnel shortly after server integration testing is concluded at the host site. This training consists instructor-led training and hands-on training.  The trainer will also return to the site shortly before training begins to reinforce the hands-on training and assist with user account creation as required.  Each host will be contacted by the SAIC Field Operations Manager to schedule this training.  Systems Administration personnel from satellite MTFs are strongly encouraged to attend the training conducted at the host site.
6.3.4. Client Administrator Training

Client Administrator training is provided to all sites. It is recommended that this training be conducted during the first week of end user training. Training early and working with contract technical staff allows sustainment personnel to be best prepared to support the system after I&T vendor support staff depart. If the Host Site triages trouble tickets for Satellites, Host Site help desk personnel should attend this training with satellite personnel. In this manner, issues pertaining to CHCS II workstations or client software (KEA, Tivoli, etc.) may be resolved more efficiently. 

The MTF Facility Training Coordinator coordinates the scheduling of Client Administrator students for these classes. 


6.3.5. Train-the-Trainer Training (T3)

Train-the-Trainer training is comprised of 40 hours of interactive classroom training and active participation in the OJT activities provided by the I&T vendor across the MTF.  As with client administrator training, it is recommended that the site select these individuals early in the pre-implementation phase and schedule their training first in the training schedule.  By so doing, these individuals have a longer period of time to learn the system while I&T subject matter expert personnel are available to augment their learning experience.
6.4. Implementation Assistance

Implementation Assistance consists of general and specific support activities at CHCS II designated point-of-care delivery sites. Providers receive On-The-Job-Training (OJT) after completing classroom training.  Other users in the clinic are assisted at their workstations by IAs for four weeks post classroom training. During implementation, it is recommended that patient appointments are blocked in a manner that permits all facility staff, including clerical, nursing, technicians, and especially providers, the time to learn use CHCS II to record all information about the patient encounter and to integrate use of the system into their clinical workflow. 

7. Operations and Sustainment Activities

It is exceptionally important that the Chief, Information Management Division or Chief, Medical Information Division and the MTF Project Officer work with the I&T vendor to begin transition planning on or before the first day of training.

Upon the completion of the last scheduled day of Implementation Assistance, the MTF transitions into sustainment whereby the site assumes responsibility for CHCS II. After an exit brief from the I&T vendor, the facility’s Project Staff has full knowledge of users trained, trouble ticket status, status of CHCS II build, training materials, end user device status log, and other resource. Ongoing support activities, including sustainment training activities and MHS Help Desk support, are described below. 

7.1. Sustainment Training

The facility is responsible for conducting sustainment training after clinics are activated and all available clinic personnel have been trained. Sustainment training includes training of incoming personnel and refresher training. The CITPO provides each facility with a set of training materials and manuals for sustainment training. Updates to these materials are planned to ensure they reflect the current CHCS II release functionality.


7.2. Notification of CHCS II Downtimes or System Degradation


7.1.1. CHCS II Scheduled Downtimes
CHCS II Scheduled Downtimes are coordinated through the Medical Infrastructure - Configuration Control Board (MI-CCB).  All scheduled downtimes are approved by the CITPO Program Manager and once approved, are broadcast to the field via electronic mail notification.  Every MTF should have at least one representative monitoring email for these notifications.  Requests for membership in this email distribution group can be sent to MI-CCB@nocc.disa.mil.


7.1.2. CHCS II Unscheduled Downtimes

MTF Sustainment personnel are required to provide notification of all unscheduled downtimes and system degradation for CHCS I or CHCS II through the Infonet Downtime Reporting System (DRS).  DISA will use this same mechanism for notifying sites of unscheduled downtimes and/or system degradations for Failure Mode 1 (Clinical Data Repository) and for Failure Mode 2 (Wide Area Network).  Individuals who would like to be added to these distribution groups can contact their Service Liaison at the Deployment Operations Center.
7.1.3. Release Management of CHCS II 

The Release Management team in conjunction with CITPO, TIMPO, DISA, Developmental Test & Evaluation (DT&E) Team and the software developers, plan and schedule the testing and deployment of software releases.  These include weekly software upgrades and beta tests for new CHCS II builds. Beta tests are employed to field test new functionality prior to release to the user community.  Notices of these scheduled activities are sent out through the MI-CCB notification process (see paragraph 7.1.1. above). 
7.2. MHS Help Desk/Tier Support

Subsequent to activation, the facility continues to be supported via the MHS Help Desk. The MHS Help Desk uses a 3-Tier system to ensure that corrective action is accomplished at the lowest possible while providing timely and cost-effective maintenance support to the end user. 

Tier 0:  Tier 0 problems are resolved by local site support personnel, generally through the MTF help desk. Problems addressed by Tier 0 usually are application-driven and relate predominantly to training and education requirements. Entry-level assistance is provided to the user by system specialist and site managers. Tier 0 problems often involve username/password issues or error messages that can be resolved on-site. 

Tier 1: CHCS II problems which cannot be resolved by the MTF help desk Tier 0 are escalated by help desk personnel to Tier 1 support engaging the MHS Help Desk via telephone support (phone numbers provided below). The MHS Help Desk generates a trouble ticket, addresses the problem with the user, and closes the trouble ticket if possible. Examples of Tier 1 problems may include Visual Basic or Tuxedo error messages that cannot be resolved by the system administer on-site. If a trouble ticket cannot be resolved with Tier 1 expertise it is escalated by the MHS Help Desk to Tier 2 support personnel. 

Tier 2: Tier 2 support personnel at the MHS Help Desk have technical expertise with component knowledge and the trouble-shooting capability to resolve problems beyond Tier 1. Tier 2 problems may involve known errors that are in the process of being resolved, in which case the MHS Help Desk personnel may give a work-around solution until ticket is closed or escalated. If the MHS Help Desk is unable to resolve the trouble ticket at Tier 2, it is escalated to the appropriate support vendor. 

Tier 3: CHCS II problem that cannot be resolved by the MHS Help Desk are escalated to the system developer who provides Tier 3 support. Tier 3 issues generally involve either a material defect in the software that is affecting the functionality of the system or a user’s desire to change or enhance a software feature. The issue is investigated by system developer staff and results in either a (1) Problem Change Request or (2) System Change Request. The MHS Information Management Directorate manages this process. Problem Change Requests are forwarded to the CITPO Configuration Management Workgroup for prioritization and repair. System Change Requests represent an enhancement to baseline system functionality and by MHS policy must be prioritized and funded by a Tri-Service panel. 

MHS Help Desk Contact Information: 

The MHS Help Desk (Tiers 1 and 2) Customer Support Telephone Numbers are: 

CONUS Site: 

(800) 600-9332

OCONUS Sites:
(866) 637-8725

Direct Commercial:
(210) 767-5250

Commercial Fax:
(210) 767-0449

The MHS Help Desk Internet web site http://www.mhs-helpdesk.com includes a frequently asked question section and links to allow users to request accounts, enter trouble tickets or query the status of open tickets. 

8. In Closing

Your comments on this guide and other CHCS II implementation materials are critical to our ability to improve upon these documents. Please submit any recommended changes for this guide or any other CHCS II implementation materials to the Deployment Operations Center at CITPO-OPSCTR@ha.osd.mil.

Please take advantage of the Deployment Operations Center electronic library online at: www.citpo.ha.osd.mil. The companion documents listed in Appendix C are currently available in the library. If you have recommendations for additional resources that should be added to the library, please notify the Deployment Operations Center by calling 703-284-7400 or 866-837-1924.

Appendix B provides contact information for Service and CITPO CHCS II points of contact. These individuals, as well as the Deployment Operations Center, are important resources for you throughout the CHCS II implementation process. 

APPENDIX A: Drivers for Development of CHCS II

The Department of Defense (DoD) and the MHS require a worldwide integrated clinical information system to meet strategic goals and mission requirements. CHCS II is the major information technology enabler to support the MHS critical mission tenets of Force Health Protection (FHP) and Population Health Improvement (PHI). FHP is an integrated, prevention-oriented and surveillance-based clinical system for maintaining a healthy and fit force and for casualty prevention. FHP directly supports the medical readiness of every Soldier, Sailor, Airman and Marine for all military operations. PHI applies to the FHP activities for maintaining a healthy and fit population while optimizing clinical outcomes across the MHS by shifting from an emphasis on disease and injury intervention to prevention and health promotion. The target for PHI includes all members of the military community: armed forces members, their families and other entitled to DoD medical care. Collectively, FHP and PHI will reduce the requirement for complex health care in the patient population and costly health care interventions while maintaining a more combat capable force. 

In 1991 the Institute of Medicine (IOM), a congressionally chartered advisor to the Federal government on scientific and technological matters, published its report, The Computer-based Patient Record: An Essential Technology for Health Care.
The IOM committee identified the following five objectives for future patient record systems: 

1) Support patient care and improve its quality

2) Enhance the productivity of health care professionals and reduce the administrative costs associated with health care delivery and financing. 

3) Support clinical and health services research. 

4) Accommodate future developments in health care technology, policy, management, and finance. 

5) Establish mechanisms to ensure patient data confidentiality at all times. 
The IOM determined that future patient records must be computer based if these objectives were to be obtained. However, they noted any efforts to automate the form, content, and procedures of current patient records would perpetuate deficiencies and would not be sufficient to meet emerging user needs. To be successful, the computer-based patient record must reside in a practitioner reminders and alerts, clinical decision support systems, links to bodies of medical knowledge, and other aids. 

The introduction of the CPR concept coincided with the deployment of U.S. troops in Operation Desert Shield/Desert Storm. In 1992, complaints from Service members experiencing unexplained illnesses and other health problems following deployment to the Persian Gulf drove the White House and Congress to call for investigation. Public Law 102-585, Sec 706 mandated that the Secretaries of the DoD and the Department of Veterans Affairs enter into an agreement with the National Academy of Sciences – specifically IOM’s Medical Follow-Up Agency (MFUA) – to review health consequences of military service in the Persian Gulf theater of operations during the Persian Gulf War. 

The MFUA Committee to Review Consequences of Services During the Persian Gulf War published its final report, Health Consequences of Service During the Persian Gulf War: Recommendations for Research and Information Systems, in 1196. The report recommended development of a “uniformed medical record”. The report stated the “single most troublesome problem encountered in attempts to conduct epidemiologic studies of illnesses among [Persian Gulf War] veterans has been the inability to retrieve information on medical care events such as hospitalization, outpatient visits, and diagnoses and treatments from DoD and DVA medical records in a uniform and systematic manner.” The report went on to say the “lack of uniform and retrievable medical information concerning reserve, National Guard, active, and separated forces has greatly inhibited systematic analysis of the health effects of mobilization…Current systems are fragmented, disorganized, incomplete, and therefore poorly suited to support epidemiologic and health outcome studies.” 

During the same time period, the President established the Presidential Advisory Committee on Gulf War Veterans’ Illnesses. The Advisory Committee was charged with the identification of relevant actions that make be taken by the federal government to better safeguard the health and wellbeing of the US Armed Forces. 

In response to the committee’s special report the President issued the following direction:

“I am directing the Department of Defense and Veterans Affairs to create a new Force Health Protection (FHP) Program. Every Soldier, Sailor, Airman and Marine will have a comprehensive, lifelong medical record of all illnesses and injuries they suffer, the care and inoculations they receive and their exposure to different hazards. These records will us prevent illness and identify and cure those that occur”

Congress supported the President’s direction by specifically addressing FHP requirements in the Fiscal Year 1998 DoD Authorization Act (Public Law 105-85, Section765). Public Law 105-85 required the Secretary of Defense to establish a system to assess the health condition of members of the Armed Forces deployed outside the U.S. as part of contingency or combat operations. 

These events and studies made clear the need for an organized electronic CPR. In November 1996, the Assistant Secretary of Defense (Health Affairs) approved the Mission Needs Statement (MNS) for the CHCS II. The MNS stated the need to implement a worldwide, single, integrated clinical information system. CITPO, the acquisition officer for all centrally managed clinical information technology systems that support the delivery of health services throughout the MHS, was charged with acquiring and implementing the Military CPR. 

In 2003, following a thorough acquisition process, exhaustive developmental and operational testing and a limited deployment to Army, Navy, and Air Forces facilities, CHCS II was approved for worldwide deployment. Worldwide deployment of CHCS II is to commence in January 2004 and rollout is expected to occur over a 30-month period.  

APPENDIX B: Points of Contact

	Role
	Name
	Email

	Air Force
	LtCol Fuller
	Kathryn.Fuller@pentagon.af.mil

	Navy
	CDR Sowell
	Pamela.Sowell@ha.osd.mil

	AMEDD
	LTC  Moody
	Ron.Moody@amedd.army.mil 

	CHCS II Project Officer
	CAPT Moos
	Heidi.Moos@tma.osd.mil

	CITPO Systems Deployment Director
	Col Carraher
	June.Carraher@tma.osd.mil

	CITPO Deputy Director for Implementation 

Army Liaison
	MAJ Miller
	Michael.Miller@tma.osd.mil 

	CITPO Deputy Director for Implementation 

Navy Liaison
	CDR Green
	Kristin.Green@tma.osd.mil

	CITPO Deputy Director for Implementation 

Air Force Liaison
	Maj Barker
	Leslie.Barker@tma.osd.mil

	TIMPO Program Manager
	COL Lewis
	Vaseal.Lewis@ha.osd.mil



APPENDIX C: Companion Documents

	Doc
	Companion Documents
	Organization POC

	1
	CHCS II Commander’s Guide (v 2.0)
	CITPO

	2
	Pre-Implementation Meeting (PIM) Checklist Template
	CITPO

	3
	Functional Pre-Site Survey Questionnaire (PSSQ)
	CITPO

	4
	Technical Pre-Site Survey Information Document
	TIMPO

	5
	CHCS II Host Site Responsibilities
	Under revision

	6
	Server Installation and Integration Testing Documents 
	TIMPO

	7
	DD 2875 Instructions
	CITPO

	8
	Common User Roles
	CITPO

	9
	Account Creation Procedures
	CITPP

	10
	CHCS II Device Placement Criteria
	TIMPO


Online Access to Companion Documents: The Deployment Operations Center established an electronic library of all implementation-related documents. Log on to the CITPO intranet at www.citpo.ha.osd.mil. Click on the yellow Register bar in the upper right hand corner of the site to register for access to the Deployment Operations Center content. 
Please note that the companion documents listed above are considered live documents and undergo revisions frequently. Please contact the Deployment Operations Center with any questions. 



























� White House Memorandum dated 8 November 1997





