## Slide 1: Patient-Centered Medical Home and Secure Messaging
CAPT Bob Marshall, MC USN
Chief Medical Informatics Officer
Travis Szabo, PMP
Secure Messaging Project Manager

## Slide 2
Learning Objectives
Describe and discuss the patient-centered medical home (PCMH)
Describe the concept and execution of secure messaging (SM)
Describe how SM affects care and supports the clinical and regulatory aspects of the PCMH
Describe secure messaging services and how they fit into the Medical Home model
Describe key lessons learned from the Navy implementations so far, including progress metrics, lessons learned, and user feedback
Directly address several common misunderstandings about the impacts of secure messaging
2

## Slide 3: PCMH – What is it?
The Patient-Centered Medical Home (PCMH) - an approach to providing comprehensive primary care for children, youth and adults
The PCMH is a health care setting that facilitates partnerships between individual patients, and their personal physicians, and when appropriate, the patient’s family
The PCMH applies across the continuum of care. For DOD personnel, that includes the DOD and VA medical systems…as well as purchased care (Network providers)
The PCMH concept and execution is a component of “Digital Health Reform” – Improving Health by leveraging technology to the patient

## Slide 4: PCMH Concepts
Personal physician - each patient has an ongoing relationship with a personal physician
Physician directed medical practice - the personal physician leads a team of individuals at the practice level who collectively take responsibility for the ongoing care of patients
Whole person orientation - the personal physician is responsible for providing for all the patient’s health care needs or taking responsibility for appropriately arranging care with other qualified professionals

## Slide 5: PCMH Concepts cont
Care is coordinated and/or integrated across all elements of the complex health care system
Quality and safety are hallmarks of the PCMH
Enhanced access to care – available through systems such as open scheduling, expanded hours and new options for communication between patients, their personal physician, and practice staff

## Slide 6
Medical Home
Port
Population
Health
Patient-Centered Care
Refocused Medical Training
Patient & Physician Feedback
Advanced IT Systems
Improved Access to Care
Team-Based
Healthcare Delivery
Decision Support Tools

## Slide 7: Secure Messaging – What is it?
SM is a method to communicate asynchronously between patients and the health care team
It is not e-mail
Two major providers: RelayHealth and Medfusion
Encrypted e-mail: Kryptiq (lacks other tools)
SaaS, Fully HIPAA-compliant, 128 bit encryption, Web-based, 2-factor authentication
Text-based messages or structured visits
Patient education and preventive health reminders
Results distribution; Network provider consults

## Slide 8: NCQA PCMH Recognition
PPC-PCMH Recognition is based on meeting specific elements included in nine standard categories:
  1. Access and Communication
  2. Patient Tracking and Registry Functions
  3. Care Management
  4. Patient Self-Management and Support
  5. Electronic Prescribing
  6. Test Tracking
  7. Referral Tracking
  8. Performance Reporting and Improvement
  9. Advanced Electronic Communication

## Slide 9: Secure Messaging and PCMH
Asynchronous communication allows more efficient and more completely documented discussions between patients and health care team
Minor problems can be discussed and managed via SM vice clinic or ED visit
Results from lab and radiology tests can be communicated with patients and coordinated
ED and consultant visits can be discussed without requiring clinic visit…or clinic visit confirmed
Network consultants can send results via SM

## Slide 10: Secure Messaging and Practice Improvement
How SM helps improve overall patient care
  Results distribution
  Reduce unnecessary clinic visits
  Medication reconciliation and F/U
  Better documentation of remote interactions
  Improved efficiency for health care team
  Improved patient and health care team satisfaction
  Patient engagement improved
  Overall improved care coordination

## Slide 11
11
How Secure Messaging
Supports Medical Home

## Slide 12: Medical Home Secure Messaging Pilots
NMC San Diego
Naval Med Ctr
Portsmouth
NNMC Bethesda
Naval Hosp
Camp Lejeune
Naval Hosp
Pensacola
Naval Hosp
Jacksonville
Naval Hosp
Bremerton
JBER
Elmendorf/Richardson
WRAMC
Quantico
Naval Hosp
Camp Pendleton

## Slide 13: Implementation Timeline
A case study in rapid deployment..
Six Navy Sites
Kickoff to completion of initial training-30 days
Six RelayHealth staff members oriented 300 users in one week
Physicians and staff received 30 minute orientation to begin using the service
With tight scheduling, 1 to 3 business days was required to complete MTF orientation (depending on size)
Notes: New paradigm with a hosted model…IA references.

## Slide 14: Connecting Patients with Their Care Team
Patient to Physician Secure Messaging includes:
Administrative Messaging
  Note to Office
  Appointments: Request and Reminder
  Referral Request
  Rx Renewal Request
  Lab Tests: Request and Result Delivery
Clinical Messaging
  Note to Provider
  Structured WebVisit®
  Template Management for Patient Messaging

## Slide 15: Connecting Patients with Their Care Team…cont
Patient to Physician Secure Messaging includes…cont:
Broadcast messaging
Reminder Messaging
Patient Education Library
Physician to Physician Connectivity:
  Clinical Messaging for Referrals and Care Collaboration
  Health Records Sharing
Colleague to Colleague Messaging
Integrated Personal Health Records

## Slide 16: Secure Messaging Physician/Staff Home Page
The system provides physicians & staff with a suite of secure internet based applications & services to communicate with patients, connect with colleagues, and coordinate care across the care team and community.
Providers and staff can:
Offer patients improved access and service
Send patient lab results electronically
Conduct online WebVisit®
Push reminders and alerts
Access and share a patient’s Personal Health Record
Integrate these services with workflow and process to gain efficiency and improve productivity
Demonstrate measurable returns

## Slide 17: NNMC Online https://www.bethesda.med.navy.mil/nnmconline/
Notes: This is the portal or entry point that the medical center are directing patients. From here they can sign in or register.

## Slide 18: Navy Medical Home
Notes: This is the portal or entry point that the medical center are directing patients. From here they can sign in or register.

## Slide 19
Chart: Navy Medical Home Enrollment May 2009 - Nov 2010
| 39934 | 39965 | 39995 | 40026 | 40057 | 40087 | 40118 | 40148 | 40179 | 40210 | 40238 | 40269 | 40299 | 40330 | 40360 | 40400 | 40431 | 40461 | 40492
Patients Enrolled | 174 | 991 | 1679 | 1999 | 2682 | 3424 | 3869 | 4227 | 4483 | 4670 | 4920 | 5132 | 5406 | 5738 | 6037 | 6761 | 7525 | 9432 | 11914
Providers Enrolled | 52 | 52 | 53 | 55 | 76 | 76 | 79 | 79 | 79 | 79 | 78 | 78 | 80 | 82 | 84 | 398 | 419 | 473 | 480
Six Pilot Sites Go Live
Patient Enrollments Ramping

## Slide 20
Chart: Navy Medical Home Messaging Breakdown May 2009 - Nov 2010
| Appointment Request | Rx Refill Request | Lab Result Request | Referrals | Note to Doc | Admin | Web-Vsits
Total | 2434 | 2037 | 1771 | 137 | 10151 | 1837 | 131

## Slide 21: Lessons Learned
Create the vision: First months of implementation are culture change
Build a Coalition: Leverage early adopters/physician champions
Communicate the Vision: Frequent Marketing & Communications are key to BOTH physician/ staff awareness & patient adoption
Notes: John Kotter (Harvard Professor)…organization change.

## Slide 22: Lessons Learned…cont
Early Wins: Continuous outreach and education help providers and teams understand advantages and see results
  Vital to ensure “credit” is recognized
Value Prop: Referral management to network providers is a high value transaction; users also site greater efficiency
Enhancements: Data exchange and tighter integration with the ambulatory record will simplify the process

## Slide 23: User Feedback
I really like the file attachment function, and I use it frequently to provide patients with rehab exercises or scans.
Things are going very smoothly; the system is so easy – just like using email only more secure.
When I train on this, I just get them to logon and in 15 minutes, they say “this is so easy”!
The time savings from alleviating telephone tag are huge.
The documentation advantage is huge.

## Slide 24
Myth 1: It will cause a deluge of emails from patients and take too much time to respond
  “Not true”
  “Really not an issue here”
  “Has actually saved time overall due to less telephone tag”
Myth 2: It will take too much time to learn the system; I’ll never be able to do this
  “Ease of logon, ease of navigation”
  “Test messages worked great to show how easy it is”
  “I say ‘just log on and try it’ and you will see how easy it is”
Myth 3: It’s just the younger providers who use this
  “Most of us are already using the AHLTA, CHCS and other core systems, so we are already computer savvy. And, this is actually easier than those systems”
Myth 4: My patients are:(1) older, (2) not online (3) not tech savvy
  ePatients: 72% 18-29, 71% 30-49, 59% 50-64, 27% 65+*
  88% of US adults with internet access research health info online*
  61% of all Americans rely on internet for health info*
Secure Messaging
Source: Consumers and Health Information Technology, A National Survey (CA Healthcare Foundation, 2010)

## Slide 25: We Will Look Back…
“That it will ever come into general use, notwithstanding its value, is extremely doubtful because its beneficial application requires much time and gives a good bit of trouble, both to the patient and practitioner, because its hue and character are foreign and opposed to all our habits and associations.”
London Times in 1834, describing the stethoscope

## Slide 26: Contact Information
CAPT Bob Marshall, MC USN
Robert.Marshall@med.navy.mil
Office: 202-762-3131
Travis Szabo
Travis.Szabo@med.navy.mil
Office: 210-808-0762

## Slide 27: Backup

## Slide 28
Chart: 
| 39934 | 39965 | 39995 | 40026 | 40057 | 40087 | 40118 | 40148 | 40179 | 40210 | 40238 | 40269 | 40299 | 40330 | 40360 | 40400 | 40431 | 40461 | 40492
Provider Message | 15 | 17 | 50 | 315 | 778 | 89 | 93 | 714 | 103 | 90 | 172 | 124 | 183 | 153 | 610 | 190 | 210 | 179 | 592
Patient Message | 350 | 1382 | 1378 | 1062 | 1849 | 1823 | 1372 | 1194 | 1373 | 1031 | 1599 | 1261 | 1518 | 1891 | 1681 | 2210 | 2924 | 4481 | 5759
Staff Messages | 2 | 191 | 497 | 814 | 3732 | 2765 | 1352 | 4905 | 2082 | 3213 | 5144 | 276 | 7618 | 11329 | 4463 | 3227 | 7191 | 17788 | 10689

## Slide 29: NHP Online - Marketing

## Slide 30: NHP Online
Notes: This is the portal or entry point that the medical center are directing patients. From here they can sign in or register.

## Slide 31: Secure Login

## Slide 32: Provider / Staff View

## Slide 33: NHP Online – Patient Home Page
Appointment Requests
Prescription Renewals
Lab test Results
Notes to the staff
Online webVisits

## Slide 34: Appointments

## Slide 35: Request/Receive Lab Results

## Slide 36: webVisit Message Templates
Structured templates that guide you through a series of questions to convey your concerns to your provider in a meaningful and thoughtful manner

## Slide 37: WebVisit Heartburn

## Slide 38: Integrated PHR
Convenient secure repository for your health information

## Slide 39: Educational Resources

## Slide 40: Lessons Learned
Importance of Navy provider endorsements to drive credibility and adoption at the MTF
Patients will be most responsive to a direct physician invitation
Engage and include your office staff for maximum benefit
One of the key value propositions is the facilitation of referrals
Medical Home needs to be a part of the workflow and accepted before staff will engage in process
Collecting emails for patient invitations can be challenging, but you have to start somewhere

## Slide 41: Questions
41